## Overview
Project Overview
This document is a break down software task for door-sensor project. Hardware: + Control board: base on FreeScale Sabreq board, using Freescale IMX 6 dual lite/solo Software + Yocto linux from Linux Foundation Team Member: + Quan Cao: SW engineer + Tien Pham: SW engineer + Nhan Nguyen: SW engineer

## Basic Function
Module | Sub-module | Description | Owner | Status | Estimate | Comment
Study Yocto | Build image | Work with Wandboard or Qemu Emulator | Tien, Nhan | Inprogress | 2014-10-31
Yocto environment |  | Bitbake buid framework to build bootable image | Quan | DONE
Board Bring up | Uboot | Init DDR bootable Boot kernel | Quan | NA
Kernel Driver | Build device tree for control board |  | ??
| GPIO control button |  | ??
| GPIO control led |  | ??
| USB component |  | ??
| SPI NOR |  | ??
| Battery Control |  | ??
Application Deamon | Gnokii module | + Send/receive sms + Phone call + Work with z-wave daemon (UNIX socket) | Quan | 60%
| Z-wave server | + Work with Z-wave module via Serial API + Communicate with Gnokii (UNIX socket) + Button | Quan | NA
| Watch dog + board monitor server | + Monitor battery, power, control status leds | Tien, Nhan

## Enhance Feature
Module | Sub-module | Description | Owner | Status | Estimate | Comment
HDMI |  | Graphics
Audio
Power regulator |  | Low energy when run on Battery
Mass production firmware |  | How to burn firmware for mass production
BLE + Wifi combo